## Sheet1
As a(n) | I want to... | so that... | Priority | Status | Sprint Number | Task Time | Team Member(s)
App User | be presented with puzzles that involve data structures | I can learn about basic Data Structures | 8 | in progress | 2 | 10 hours/12 hours | Everyone
Administrator | have a login interface | I can access my account | 7 | done | 1 | 12 hours
Administrator | be able to manage student accounts | I can add/remove student accounts | 7 | partially done | 1 | 12 hours | Zak/Torie
App User | have an intuitive interface | I can use the app in a more natural way | 4 | in progress | 1 | 12 hours | Zak/Tyer
App User | be able to sign up for an account | I can save my progress | 7 | done | 1 | 12 hours | Zak/Tyler/Torie
App User | be able to access my data from multiple devices | I can play on different platforms | 7 | done | 1 | 12 hours
Developer | have a UML representation to follow | We can have a common design | 7 | done | 1 | 12 hours | Chris, Torie
Administrator | run analytics for 1 or many students | I can aggregate data | 7 |  | 1.2.3 | 6 hours
Administrator | run and view analytics in a browser compatible format | I can view and return a summary back to the client | 5 |  |  |  | Meysam
Administrator | have administrator software that is intuitive | I can easily use the software | 3
Administrator | send results through the network | I can easily distribute results | 5
Administrator | be able to change the difficulty of the app per student | I can simulate different phases | 5
App User | be challenged (or engaged) | I will be motivated for continued use of the app | 4
App User | Learn about basic Data Structures | I can be a better computer scientists when im older | 8
App User | have a graphical representation of what I am learning about | I feel like the app is more lively | 6 | In progress | 2 | 12 hours | Tyler/Torie/Chris
App User | have an auto-save feature | I don't have to worry about saving | 3
App User | have a brief(optional) tutorial | I can learn how to use the app | 6
App User | be able to progress through different levels | I can learn about more than one thing | 3
App User | replay previously completed levels | I can review and practice with specific structures | 6
App User | be able to get help or a hint on the current puzzle | I do not become frustrated and lose interest | 3